# Project Plan and Risk Management

Project: Global Health Insights: An End-to-End Analysis of Global Health Statistics
Version: 1.0 (28 October 2026)
Project Leader: Ahmed Ragab Ali Mohammed Aboelanen

# 1. Project Plan

The plan targets internal deadlines about one week before the official deadlines (6 November for analysis and design, 30 November for implementation, and 4 December for final presentation, testing, and reports). Status values should be updated as work progresses.

| ID | Task | Start | End (internal) | Official deadline | Output | Status |
| --- | --- | --- | --- | --- | --- | --- |
| T1 | Planning documents (plan, roles, risks, KPIs) | 28 Oct | 29 Oct | 16 Oct (overdue) | 00_project_plan, 00_roles_and_responsibilities | In progress |
| T2 | Requirements gathering | 26 Oct | 27 Oct | 16 Oct (overdue) | 00_requirements | Done |
| T3 | Data inspection and quality assessment | 25 Oct | 27 Oct | n/a | 01_inspect.py, data quality assessment | Done |
| T4 | Analysis and design documents | 26 Oct | 29 Oct | 6 Nov | Problem statement, data model, data flow, wireframes | Done (final review) |
| T5 | Python: data cleaning and transformation | 30 Oct | 5 Nov | 30 Nov | 02_clean.py, cleaning log, cleaned_data.csv | Not started |
| T6 | Python: exploratory analysis | 5 Nov | 8 Nov | 30 Nov | 03_eda.py, EDA charts | Not started |
| T7 | SQL: database and star schema tables | 6 Nov | 10 Nov | 30 Nov | 01_create_database.sql, 02_create_tables.sql | Not started |
| T8 | SQL: data load, analytical queries, and views | 10 Nov | 14 Nov | 30 Nov | 03_load_data.sql, 04_analysis_queries.sql, 05_views.sql | Not started |
| T9 | Power BI: connection, data model, and DAX measures | 14 Nov | 17 Nov | 30 Nov | Power BI file (data model) | Not started |
| T10 | Power BI: dashboard pages | 17 Nov | 20 Nov | 30 Nov | Power BI file, screenshots, PDF | Not started |
| T11 | Tableau Public dashboard | 18 Nov | 22 Nov | 30 Nov | Published dashboard link, screenshots | Not started |
| T12 | Cross-tool validation | 22 Nov | 25 Nov | 4 Dec | Validation table, bug log | Not started |
| T13 | Documentation: user manual, technical documentation, data dictionary | 23 Nov | 27 Nov | 4 Dec | Three documents | Not started |
| T14 | Presentation and infographic | 24 Nov | 27 Nov | 4 Dec | Presentation, infographic | Not started |
| T15 | GitHub organization and README | 27 Nov | 29 Nov | 30 Nov | Complete repository | Not started |
| T16 | Final review and rehearsal | 30 Nov | 3 Dec | 4 Dec | Final package | Not started |

The final discussion takes place in week 21 (date to be confirmed with the lecturer); attendance is mandatory.

Priority order if time becomes limited:

- Must: T5 to T8 (Python and SQL), T10 core pages (Overview, Disease Burden, Healthcare Capacity, Mortality and Recovery, Trends), T12 (validation), T15 (GitHub and README).

- Should: T11 (Tableau), T13 (documentation), T14 (presentation).

- Could: Power BI pages Socioeconomic and Treatment.

# 2. Estimated Effort

| Area | Estimated hours |
| --- | --- |
| Python: cleaning and exploratory analysis | 12 |
| SQL: database, queries, and views | 12 |
| Power BI | 15 |
| Tableau | 10 |
| Cross-tool validation | 4 |
| Documentation | 10 |
| Presentation and infographic | 6 |
| GitHub and README | 4 |
| Planning and design (remaining review) | 6 |
| Total | 79 |

The estimate assumes about 2.5 to 3 hours of work per day between 28 October and 27 November. Task ownership is recorded in the Roles and Responsibilities document, and individual contributions are recorded in the README.

# 3. Risk Assessment

Scoring: likelihood and impact are rated Low (1), Medium (2), or High (3); score = likelihood x impact.

| ID | Risk | Likelihood | Impact | Score | Mitigation |
| --- | --- | --- | --- | --- | --- |
| R1 | Team members withdraw or have limited availability | 3 | 3 | 9 | Onboarding task to confirm availability; continuity rule in the Roles document; keep at least four members on the team; record contributions honestly; Project Leader can cover the critical path |
| R2 | Large scope (four tools, seven dashboard pages) compared with the available time | 3 | 3 | 9 | Internal deadlines one week earlier; priority order (Must, Should, Could); build the core pages first |
| R3 | Dependence on a single person for critical tasks | 2 | 3 | 6 | All files stored on GitHub and OneDrive; scripts commented; steps documented so another member can continue |
| R4 | Inconsistent figures across Python, SQL, Power BI, and Tableau | 2 | 3 | 6 | Fixed measure definitions; selected validation metrics; early comparison of a few metrics before building all pages |
| R5 | Dashboard viewers misinterpret results because the dataset is synthetic | 2 | 2 | 4 | Synthetic-data notice on every dashboard and slide; Data Quality Assessment; lecturer informed and approved |
| R6 | Raw data file (134.4 MB) exceeds the GitHub 100 MB file limit | 3 | 2 | 6 | Do not store raw or cleaned data in the repository; provide the dataset link and a small sample; check the Power BI file size |
| R7 | Memory or performance problems with one million rows | 2 | 2 | 4 | Use compact data types in Python; load data once; use aggregated SQL views for dashboards |
| R8 | Tool installation or licensing problems (SQL Server, Power BI is Windows-only, Tableau Public publishes publicly) | 2 | 2 | 4 | Use free editions (SQL Server Express or Developer, Tableau Public); test tools in the first week; publish only non-sensitive data |
| R9 | Loss of files or synchronization conflicts | 1 | 3 | 3 | OneDrive plus GitHub; a weekly extra copy of key files |
| R10 | Lecturer feedback changes requirements late | 2 | 2 | 4 | Version the documents; confirm key decisions with the lecturer in writing |

# 4. Key Performance Indicators

The examples in the guidelines (response time, uptime, adoption) apply to software systems, so the indicators below are adapted to a data analytics project.

| ID | KPI | Target | How measured |
| --- | --- | --- | --- |
| K1 | Official deadlines met | 3 of 3 (6 Nov, 30 Nov, 4 Dec) | Delivery dates compared with the plan |
| K2 | Internal deadlines met | At least 80% of tasks T1 to T16 | Plan status review each week |
| K3 | Rows loaded into the database | 1,000,000 (equal to the cleaned file) | Row-count check at load |
| K4 | Cross-tool validation match rate | 100% of selected validation metrics | Validation table |
| K5 | Analytical questions answered | 8 of 8 with at least one table or visual | Question-to-visual mapping |
| K6 | Dashboards delivered | Power BI core pages (at least 5 of 7) and one Tableau dashboard | Review of delivered files |
| K7 | Synthetic-data notice | Present on 100% of dashboard pages and slides | Visual review |
| K8 | Dashboard responsiveness | Visuals refresh within about 5 seconds after a filter change | Manual timing test |
| K9 | Open bugs at submission | 0 open items in the bug log | Bug log |
| K10 | Reproducibility | Scripts run end-to-end after changing only the file path | Test run on a second computer or a clean folder |
| K11 | Repository completeness | All planned deliverables uploaded; README includes a contribution table | Repository checklist |