# Roles and Responsibilities

Project: Global Health Insights: An End-to-End Analysis of Global Health Statistics
Version: 1.0 (draft, October 2026)
Project Leader: Ahmed Ragab Ali Mohammed Aboelanen
Status: Roles will be finalized by 31 October 2026.

# 1. Team

| Member | Role |
| --- | --- |
| Ahmed Ragab Ali Mohammed Aboelanen | Project Leader |
| Shahad Tarek Mohammed Sharaf | To be assigned |
| Dalia Mohamed Gouda Al_Sayed | To be assigned |
| Mohamed Kamal Said Abdelrehim Kamal | To be assigned |
| Aya Abdelaziz Ibrahim Mohammed | To be assigned |
| Louka Mokhles Meladh Azer | To be assigned |

# 2. Work Areas and Owners

| Area | Description | Primary owner | Backup |
| --- | --- | --- | --- |
| Python | Data cleaning, transformation, and exploratory analysis | TBD | TBD |
| SQL | Database, star schema, analytical queries, and views | TBD | TBD |
| Power BI | Interactive dashboard (seven pages) | TBD | TBD |
| Tableau Public | Complementary dashboard | TBD | TBD |
| Documentation and testing | Data dictionary, validation table, bug log, user manual, technical documentation | TBD | TBD |
| Presentation | Final presentation, infographic, demo video (optional) | TBD | TBD |
| Project leadership | Planning, coordination, LMS submissions, GitHub repository | Ahmed Ragab Ali Mohammed Aboelanen | TBD |

# 3. Deliverables by Area

| Area | Deliverables | Internal deadline |
| --- | --- | --- |
| Python | 02_clean.py, 03_eda.py, cleaned_data.csv, cleaning log, EDA charts | 8 Nov 2026 |
| SQL | SQL scripts 01 to 05 (database, tables, load, queries, views) | 14 Nov 2026 |
| Power BI | Power BI file (.pbix), page screenshots, PDF export | 20 Nov 2026 |
| Tableau Public | Published dashboard link, screenshots | 22 Nov 2026 |
| Documentation and testing | Validation table, bug log, user manual, technical documentation | 27 Nov 2026 |
| Presentation | Presentation, infographic | 27 Nov 2026 |
| Project leadership | Planning documents, GitHub uploads, README contribution table | Ongoing |

Official deadlines: implementation 30 November 2026; final presentation, testing, and reports 4 December 2026.

# 4. Hand-offs Between Areas

| From | To | Hand-off | Check before handing over |
| --- | --- | --- | --- |
| Python | SQL | cleaned_data.csv and the cleaning log | Row count is 1,000,000; column names match the column mapping in the data model design |
| SQL | Power BI and Tableau | SQL views (and CSV exports for Tableau) | Views return the expected row counts; view names match the design document |
| Power BI and Tableau | Documentation and testing | Dashboard figures for validation | The agreed validation metrics are visible in both dashboards |
| All areas | Presentation | Final screenshots and key findings | Dashboards are complete and show the synthetic-data notice |

# 5. Continuity Rule

Team membership may change. Once roles are final, each area has a backup. If an owner becomes unavailable or leaves the project, the backup takes over and informs the Project Leader the same day, and the Project Leader reassigns tasks within two days. The team must keep at least four members at all times.

# 6. Onboarding Task (All Members, by 30 October 2026)

- Install the required tools: Spyder, SQL Server with SSMS, Power BI Desktop, and Tableau Public.

- Download the dataset from Kaggle and run 01_inspect.py.

- Send a screenshot of the output (1000000, 22) to the team group.

The results confirm that each member is set up and available, and are used to finalize the roles.

# 7. Working Rules

- Each member delivers work to the Project Leader one day before the internal deadline.

- Files are named: work name, owner name, version (for example, clean_dalia_v1.py). The Project Leader reviews, renames to the final name, and uploads to GitHub.

- Each commit message names the owner (for example, “Add cleaning script (by Dalia)”).

- Contributions are also recorded in a contribution table in the README.

- The team meets weekly at a fixed time. [add day and time]